## Sponsor Inputs
# | High level ideas / Features
1 | Create Account
2 | View Restaurants
3 | Search Restaurants
4 | View Menu
5 | Add to Cart
6 | Purchase
7 | Restaurant views order
8 | Restaurant marks order as delivered
Notes:
1 | The above points were listed as draft ideas by the project sponsor.
2 | The project sponsor mentioned that he wants to compete against Talabat.
3 | As a sponsor, I am planning to compete against Talabat.
4 | This is a view only file, you can make a copy then edit in the copy.
5 | You can find a tab named Product Backlog Template, please feel free to use it when creating your product backlog.

## Product Backlog Template
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
As a < type of user >, I want < some goal > so that < some reason >
| Create Account | As a Consumer, I want to be able to create an account so that I could login in my account in the application. | 5 | must | 1 | Done
|  | As a Consumer, I want to be able to create an account so that I can provide my contact, location and needed information. | 5 | must | 1 | Done
| View Restaurants | As a consumer, I want to be able to view resturents so that I could see the list of restaurants I can order from. | 5 | must | 1 | work in progress
|  | As a consumer, I want to be able to view resturents ratings to that I can pick good to best rated resturants. | 4 | should | 1 | work in progress
| Search Restaurants | As a consumer. I want to be able to search resturants so that they are easier to find. | 5 | should | 1 | Work in progress
|  | As a consumer, I want to be able to search resturents in different cuisines categories so that it limits the search to certain resturents. | 4 | could | 2 | Work in progress
| View Menu | As a consumer, I want to be able to View Menu so that I could select the meal I want. | 5 | must | 2 | Work in progress
|  | As a consumer, I want to be able to View Menu best sellers so that I can try most liked meals. | 4 | could | 2 | Work in progress
| Add to Cart | As a consumer, I want to be able to add to cart so that I keep track of my purchases. | 5 | should | 2 | work in prgress
|  | As a consumer, I want to be able to add to cart so that I can order everything I want at the same time. | 5 | should | 2 | work in progress
| Purchase | As a consumer, I want to be able to purchase so that I receive my orders. | 5 | must | 3 | To be started
|  | As a consumer, I want to be able to have purchase options so that I can pick cash or card. | 5 | must | 3 | To be started
| Restaurant views order | As a Restaurant, I want to be able to view consumers orders so that I can prepare their meals. | 5 | must | 3 | To be started
|  | As a Restaurant, I want to be able to view consumers orders so that I view their information to deliver to their location. | 5 | must | 3 | To be started